## Start Here
Construction Job Costing Template
One job per file. Free from WorkHoist: workhoist.app/guides/construction-job-costing-spreadsheet-template
How to use it
1. Job Setup: enter the job, the contract value and your labor burden (payroll taxes, workers’ comp, benefits).
2. Budget: one row per cost code, with the original budget from your estimate. Everything else on that tab calculates.
3. Labor: log hours by worker and cost code, with each worker’s base pay rate. The loaded labor cost calculates from your burden.
4. Costs: log every bill, receipt and sub invoice against a cost code. Add the PO or subcontract number if there is one.
5. Commitments: log purchase orders and subcontracts when you sign them, so the budget shows what you owe before the bill arrives.
6. Change Orders: log each change with its cost and price. Only rows marked Approved move the budget and the contract.
7. WIP: enter what you have billed to date. The tab shows percent complete, earned revenue and whether the job is over- or under-billed.
Color key
Blue text = a number or entry you type in. Black text = a formula; leave it alone. Yellow fill = a setting you should check for your business.
The file ships with one sample job (an electrical sub) so you can see it working. Delete the blue sample entries on each tab when you start your own job.
Google Sheets
In Google Drive choose New > File upload, then open the file with Google Sheets. The formulas are standard (SUMIFS, MAX, IFERROR) and work in both.
Sources and limits
Employer Social Security 6.2% and Medicare 1.45%: IRS Topic no. 751 (irs.gov/taxtopics/tc751).
FUTA 0.6% after the maximum 5.4% state credit, on the first $7,000 of each employee’s wages: IRS Topic no. 759 (irs.gov/taxtopics/tc759). The burden here applies it to every hour, which overstates it once a worker passes $7,000 for the year.
State unemployment and workers’ comp rates vary by state, trade and employer. The sample values are examples only; use the rates on your own notices and policy.
This is a job costing tool, not accounting, tax or legal advice. Your accountant’s numbers win.

## Job Setup
Job Setup
Blue cells are yours to change. Yellow cells are rates to check for your business.
Job name | Riverside Medical Office — electrical | Sample job
Job number | 26-014
Customer | Sample GC, Inc. | Fictional
Original contract value | 185000 | Your signed contract amount, before change orders
Retainage held by customer | 10% | Percent the customer holds back from each payment
Labor burden |  | Added on top of each worker’s base pay rate on the Labor tab
Employer Social Security | 6.2% | IRS Topic no. 751
Employer Medicare | 1.45% | IRS Topic no. 751
Federal unemployment (FUTA), after credit | 0.6% | IRS Topic no. 759: 6.0% less up to 5.4% state credit, first $7,000 of wages only
State unemployment (SUTA) | 2.7% | EXAMPLE ONLY. Use the rate on your state unemployment notice
Workers’ comp, as % of payroll | 8% | EXAMPLE ONLY. Your policy rate per $100 of payroll ÷ 100
Other % of payroll (GL on payroll, union dues) | 0% | Leave at 0 if none
Total percentage burden | 18.95%
Benefits, $ per hour worked | 0 | Health, retirement, paid time off, spread over hours worked
Example: a $34.00/hr worker costs you | 40.443 | per hour on this burden

## Budget
Budget
Type the cost code, description, cost type and original budget (blue). Every other column calculates.
Cost code | Description | Cost type | Original budget | Approved change orders | Revised budget | Open commitments | Actual cost to date | Projected final cost | Over / (under) budget | % of revised spent
100 | Rough-in labor | Labor | 38000 | 2400 | 40400 | 0 | 9092.538 | 40400 | 0 | 22.51%
110 | Rough-in material | Material | 26000 | 0 | 26000 | 4800 | 11500 | 26000 | 0 | 44.23%
200 | Trim-out labor | Labor | 18000 | 0 | 18000 | 0 | 0 | 18000 | 0 | 0%
210 | Fixtures and trim material | Material | 22000 | 0 | 22000 | 0 | 0 | 22000 | 0 | 0%
300 | Switchgear and service | Material | 24000 | 0 | 24000 | 23400 | 0 | 24000 | 0 | 0%
400 | Equipment rental | Equipment | 3500 | 0 | 3500 | 0 | 1150 | 3500 | 0 | 32.86%
500 | Low-voltage subcontract | Subcontract | 12000 | 0 | 12000 | 7200 | 4800 | 12000 | 0 | 40%
900 | General conditions | Other | 6500 | 0 | 6500 | 0 | 535.275 | 6500 | 0 | 8.235%
Total |  |  | 150000 | 2400 | 152400 | 35400 | 27077.813 | 152400 | 0 | 17.77%
Projected final cost = the larger of the revised budget, or actual cost plus what is still committed. Over / (under) budget compares that with the revised budget.

## Labor
Labor
One row per worker per day (or per week). Type date, worker, cost code, hours and base pay rate. Loaded rate and cost calculate from Job Setup.
|  | Totals | 248 |  |  | 9627.813
Date | Worker | Cost code | Hours | Base pay rate ($/hr) | Loaded rate ($/hr) | Labor cost
2026-09-14 | Journeyman A | 100 | 40 | 38 | 45.201 | 1808.04
2026-09-14 | Journeyman B | 100 | 40 | 36.5 | 43.4168 | 1736.67
2026-09-14 | Apprentice C | 100 | 40 | 22 | 26.169 | 1046.76
2026-09-21 | Journeyman A | 100 | 38 | 38 | 45.201 | 1717.638
2026-09-21 | Journeyman B | 100 | 40 | 36.5 | 43.4168 | 1736.67
2026-09-21 | Apprentice C | 100 | 40 | 22 | 26.169 | 1046.76
2026-09-21 | Foreman D | 900 | 10 | 45 | 53.5275 | 535.275
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Costs
Costs
Every bill, receipt and sub invoice that is not payroll. Add the PO or subcontract number if there is one, so it draws down the commitment.
|  |  |  | Total | 17450
Date | Vendor | Cost code | Description | PO / subcontract # | Amount
2026-09-10 | Supply House A | 110 | Rough-in wire and boxes, first delivery | PO-1002 | 9200
2026-09-16 | Supply House A | 110 | Counter purchase, fittings |  | 2300
2026-09-18 | Rental Yard B | 400 | Scissor lift, 2 weeks |  | 1150
2026-09-25 | Low-Voltage Sub C | 500 | Progress bill 1 | SUB-01 | 4800

## Commitments
Commitments
Purchase orders and subcontracts, logged when signed. Billed to date pulls from the Costs tab by PO / subcontract number.
PO / subcontract # | Vendor | Cost code | Type | Committed amount | Billed to date | Still open
PO-1001 | Supply House A | 300 | Purchase order | 23400 | 0 | 23400
PO-1002 | Supply House A | 110 | Purchase order | 14000 | 9200 | 4800
SUB-01 | Low-Voltage Sub C | 500 | Subcontract | 12000 | 4800 | 7200
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0

## Change Orders
Change Orders
Log every change, priced or not. Only rows with status Approved move the budget (cost) and the contract (price).
CO # | Description | Cost code | Status | Cost impact | Price to customer
CO-01 | Add six circuits in suite 120 | 100 | Approved | 2400 | 3600
CO-02 | Relocate panel LP-2 | 100 | Pending | 1800 | 2700

## WIP
Work in progress (WIP)
Enter billed to date (blue). Everything else calculates. Percent complete is cost to date over projected final cost.
Original contract value | 185000 | From Job Setup
Approved change orders (price) | 3600 | Approved rows on the Change Orders tab
Revised contract value | 188600
Projected final cost | 152400 | Budget tab total
Cost to date | 27077.813 | Budget tab total: labor plus costs
Percent complete | 17.77% | Cost to date ÷ projected final cost (cost-to-cost method)
Earned revenue | 33509.682 | Percent complete × revised contract
Billed to date | 52000 | Total of your pay applications or invoices, before retainage
Over-billed | 18490.318 | Billed ahead of the work. You are holding the customer’s money
Under-billed | 0 | Work done but not billed. You are financing the job
Retainage held by customer | 5200 | Billed to date × retainage %
Projected gross profit | 36200 | Revised contract − projected final cost
Projected gross margin | 19.19%