## Start Here
WORKHOIST Retainage Tracker · Start Here
Free Retainage Tracker
One job per file. Free from WorkHoist, construction management software · workhoist.app/guides/retainage-tracking-spreadsheet-template
What it does
Retainage runs two ways on most jobs. Your client holds some of every payment back from you, and you hold some back from your subs. This file tracks both, pay application by pay application, and tells you three things: how much is still held from you and when it is due back, how much you are holding for your subs, and what you owe them out of any release you have already received.
How to use it
1. Job Setup: the contract value, the retainage rate in your contract, any cap, the completion date, and the release deadlines that apply to you.
2. Held From You: one row per pay application you send. Type the amount billed for the period (work completed plus stored materials). Retainage calculates. When a release arrives, add a row with the amount and the date.
3. Subs: one row per subcontract you hold retainage on, with its rate.
4. Sub Retainage Log: one row per pay application each sub sends you. Retainage calculates from the rate on the Subs tab. When you pay a sub their retainage, log the amount and the date.
5. Release Checklist: what you need before your client releases retainage, and before you release your subs’.
6. Summary: read it before every pay application and every week once the job is complete.
Colours
Blue text is what you type.
Black text is a formula. Leave it alone.
Yellow cells are settings. Check them against your contract before you start.
Clearing the sample
The file comes with a sample job filled in so you can see every number working. To start your own, delete the blue entries on each tab. Do not delete rows or the black formula columns.
This is not legal advice
How much retainage can be held, and when it has to be released, is set by your contract and by the law where the job is. The sample uses California’s rules for private work on a contract signed in 2026 as one worked example: a 5% cap, 45 days for the owner to pay retention after completion, and 10 days to pass each sub their share. Your state and your contract may say something different. Check them, and talk to a construction attorney before relying on a deadline.
Where it stops
One job per file, kept up to date by one person. The guide this template comes with explains when that stops being enough: workhoist.app/guides/retainage-tracking-spreadsheet-template

## Summary
WORKHOIST Retainage Tracker · Summary
Job: Lakeside Dental clinic remodel (sample)
Retainage held from you
| Contract value to date | 658500 | Original contract plus approved change orders.
| Billed to date | 658500
| Retainage withheld from you to date | 32925
| Released to you to date | 12000
| Still held from you | 20925 | Money you have earned and billed that your client is still holding.
| Withheld as a share of the contract to date | 5%
| Cap check | Within the cap | Compares retainage withheld to date with the cap on Job Setup, as a share of the contract to date.
| Completion date | 2026-09-18 | From Job Setup.
| Your release is due by | 2026-11-02 | Completion date plus the days on Job Setup.
| Status | Due in 26 days | Counts from today’s date.
| Last release you received | 2026-09-29 | The latest date on the Held From You tab.
Retainage you hold from your subs
| Withheld from subs to date | 9900
| Paid to subs to date | 0
| Still held from subs | 9900 | Your subs’ money. It is not yours to spend.
| Their share of releases you have received, not yet paid | 3608.2 | Estimated pro rata. The Subs tab shows it sub by sub.
| Pay it by | 2026-10-09 | Last release received plus the days on Job Setup.
| Status | Due in 2 days
Your own money tied up
| Held from you, less what you hold for subs | 11025 | The part of the retainage held from you that is your own money rather than your subs’.
Release checklist
| Getting your release: items done | 1 of 6
| Releasing your subs’: items done | 2 of 4
Not legal advice. Release deadlines and caps come from your contract and the law where the job is; the sample’s numbers are California’s for private work on a 2026 contract. Free from WorkHoist: workhoist.app/guides/retainage-tracking-spreadsheet-template

## Job Setup
WORKHOIST Retainage Tracker · Job Setup
Blue cells are yours to change. Yellow cells are settings to check against your contract and the law where the job is.
Setting | Value | Where the sample value comes from
Job name | Lakeside Dental clinic remodel (sample)
Your company | Your company name
Your client (owner, or the GC if you are a sub) | Lakeside Dental Group (owner)
Your role on this job | General contractor | General contractor or subcontractor. A sub with its own subs uses every tab; a sub without them can ignore Subs and Sub Retainage Log.
Original contract value | 640000
Approved change orders to date | 18500 | Approved and signed only. Update it when a change order is approved.
Contract value to date | 658500 | Calculates.
Retainage rate in your contract | 5% | Sample: 5%. California caps retention on private work at 5% for contracts entered into on or after 1 January 2026, at every tier (Civil Code 8811). Use the rate in your contract. If it changes partway through, override it on that pay application on the Held From You tab.
Cap on total retainage, as a share of the contract (blank if none) | 5% | Sample: 5%. Under Civil Code 8811 total retention on California private work may not exceed 5% of the contract price. Leave it blank if neither your contract nor your state sets one.
Completion date | 2026-09-18 | The event your release is tied to: substantial completion, completion, acceptance, or whatever your contract and state law say. Blank until it happens.
Days after completion your release is due | 45 | Sample: 45. In California an owner who withholds retention from a direct contractor must pay it within 45 days after completion of a private work of improvement (Civil Code 8812). Use your contract’s number, or your state’s if it is shorter.
Days you have to pay subs their share after you receive a release | 10 | Sample: 10. In California a direct contractor must pay each sub its share within 10 days after receiving all or part of a retention payment (Civil Code 8814). Use your contract’s number, or your state’s.
Today | 2026-10-07 | Calculates. Every “due in” and “overdue” on the Summary counts from this date.

## Held From You
WORKHOIST Retainage Tracker · Held From You
One row per pay application you send. Type the period and the amount billed (blue); retainage calculates from Job Setup. When retainage is released to you, add a row with the amount and the date it arrived.
| Totals | 658500 |  |  | 32925 | 12000
App # | Period to | Billed this period (work + stored materials) | Rate override (optional) | Rate used | Retainage withheld | Released to you | Date release received | Billed to date | Still held from you | Notes
1 | 2026-04-30 | 96000 |  | 5% | 4800 |  |  | 96000 | 4800
2 | 2026-05-31 | 142000 |  | 5% | 7100 |  |  | 238000 | 11900
3 | 2026-06-30 | 168000 |  | 5% | 8400 |  |  | 406000 | 20300
4 | 2026-07-31 | 151000 |  | 5% | 7550 |  |  | 557000 | 27850
5 | 2026-08-31 | 83500 |  | 5% | 4175 |  |  | 640500 | 32025 | Includes the $18,500 approved change order
Release | [5 empty] | 12000 | 2026-09-29 | 640500 | 20025 | Partial release on the site work, as the contract allows
6 | 2026-09-30 | 18000 |  | 5% | 900 |  |  | 658500 | 20925 | Final billing: contract billed to 100%

## Subs
WORKHOIST Retainage Tracker · Subs
One row per subcontract you hold retainage on. Type the name exactly as you will on the Sub Retainage Log. Everything after the rate calculates from that log.
Totals |  | 198000 |  | 198000 | 9900 | 0 | 9900 | 3608.2
Subcontractor | Trade | Subcontract value | Retainage rate | Billed to date | Retainage withheld to date | Released to sub | Still held from sub | Their share of releases you have received, not yet paid | Pay it by | Rate check | Notes
Bright Line Electric | Electrical | 96000 | 5% | 96000 | 4800 | 0 | 4800 | 1749.43 | 2026-10-09 | OK
Clearwater Plumbing | Plumbing | 58000 | 5% | 58000 | 2900 | 0 | 2900 | 1056.95 | 2026-10-09 | OK
Ridgeway Drywall | Drywall | 44000 | 5% | 44000 | 2200 | 0 | 2200 | 801.82 | 2026-10-09 | OK
How “their share” is worked out: of all the retainage released to you so far, each sub’s share is the retainage you withheld from them divided by all the retainage withheld from you, less anything you have already paid them. It is an estimate for planning. If your contract or the release itself names an amount for a sub, use that.
Formulas:
Pay it by = IF([Subcontractor]="","",IF(OR(I6<=0,Summary!$C16=""),"",Summary!$C16+'Job Setup'!$B16))

## Sub Retainage Log
WORKHOIST Retainage Tracker · Sub Retainage Log
One row per pay application a sub sends you. Pick the sub from the list; retainage calculates from their rate on the Subs tab. When you pay a sub their retainage, add a row with the amount and the date.
|  | Totals | 198000 |  | 9900 | 0
Date | Subcontractor | Sub’s pay app or invoice # | Billed by sub this period | Rate | Retainage withheld | Retainage paid to sub | Date paid to sub | Notes
2026-04-30 | Bright Line Electric | BLE-1 | 15000 | 5% | 750
2026-05-31 | Bright Line Electric | BLE-2 | 28000 | 5% | 1400
2026-05-31 | Clearwater Plumbing | CWP-1 | 12000 | 5% | 600
2026-06-30 | Bright Line Electric | BLE-3 | 30000 | 5% | 1500
2026-06-30 | Clearwater Plumbing | CWP-2 | 20000 | 5% | 1000
2026-07-31 | Bright Line Electric | BLE-4 | 18000 | 5% | 900
2026-07-31 | Clearwater Plumbing | CWP-3 | 18000 | 5% | 900
2026-07-31 | Ridgeway Drywall | RD-1 | 14000 | 5% | 700
2026-08-31 | Bright Line Electric | BLE-5 | 5000 | 5% | 250
2026-08-31 | Clearwater Plumbing | CWP-4 | 8000 | 5% | 400
2026-08-31 | Ridgeway Drywall | RD-2 | 22000 | 5% | 1100
2026-09-30 | Ridgeway Drywall | RD-3 | 8000 | 5% | 400

## Release Checklist
WORKHOIST Retainage Tracker · Release Checklist
What usually has to be in place before retainage is released. Your contract decides the real list: add to it, and mark what does not apply.
Getting your retainage released
Item | Applies? | Status | Date | Notes
Completion documented the way your contract defines it (certificate of substantial completion, notice of completion, or written acceptance) | Yes | Done | 2026-09-18 | Architect’s certificate of substantial completion
Punch list signed off | Yes | Requested |  | Two items left: door hardware, ceiling tile
Your lien waiver for the release amount, of the type the contract asks for | Yes | Not started |  | Conditional until the money has cleared
Lien waivers from your subs and suppliers, if the contract asks for them | Yes | Requested
Consent of surety to the release (AIA G707A or the surety’s own form), on a bonded job | No | Not needed |  | Not bonded
Closeout documents the contract lists: warranties, O&M manuals, as-builts | Yes | Requested
Final certified payroll, on prevailing-wage work | No | Not needed |  | Private job
Release requested in writing, with the documents attached | Yes | Not started |  | Send once the punch list is signed off
Before you release your subs’ retainage
Item | Applies? | Status | Date | Notes
Sub’s work accepted and their punch items complete | Yes | Done |  | All three subs
Sub’s lien waiver for the release amount received | Yes | Requested
Sub’s closeout documents received (warranties, O&M manuals) | Yes | Requested |  | Bright Line still owes panel schedules
Your own release received (in California, the 10 days to pay subs start here) | Yes | Done | 2026-09-29 | Partial release, $12,000